TROV

Internal Financial & Strategy Brief

⛔  CONFIDENTIAL — NOT FOR CLIENT DISTRIBUTION  ⛔

Antidote Group Internal Use Only  ·  Beryl + Partners

March 2026

What This Document Is For This is the internal version of the TROV proposal. It contains our real cost assumptions, actual dev spend estimates, time commitment analysis, margin thinking, and risk flags we would never show a client. Use this to align internally before any client conversation. The client-facing doc is a separate file.

# What This Actually Costs Us

Before we talk about what we charge, here is the honest breakdown of what TROV costs to deliver — in dollars, in time, and in attention. This is the foundation for every pricing decision.

## Our Actual Costs — Package A (Lean Launch)

| Cost Item | Low | High | Notes |
| --- | --- | --- | --- |
| Claude Code API usage (build phase) | $80 | $200 | 6-8 wk active build |
| Contract dev — final mile (App Store + cleanup) | $2,500 | $4,500 | 25-45 hrs @ $80-100/hr |
| Apple Developer Program | $99 | $99 | Annual |
| Supabase Pro (during build) | $50 | $100 | 2 months build |
| EAS Build, Maps API (build phase) | $0 | $80 | Free tiers cover MVP |
| Beryl time — owner build hours | 50 hrs | 80 hrs | NOT billed but real cost |
| TOTAL HARD CASH COST (excl. owner time) | ~$2,730 | ~$4,980 |  |

Margin on Package A Build We charge $10,000. Our hard cash cost is $2,730–$4,980. That's $5,000–$7,270 gross margin on the build alone — before we value Beryl's 50-80 hours. If we price Beryl's time at $150/hr (conservative for this work), that's $7,500-$12,000 in time cost, which means the build is roughly break-even to slight loss on a full-cost basis. The margin is in the ongoing retainer.

## Our Actual Costs — Package B (Full Partnership)

| Cost Item | Low | High | Notes |
| --- | --- | --- | --- |
| Dev team — LatAm via Lemon.io (3 month build) | $6,000 | $12,000 | Lead + junior, vetted |
| Dev team — US boutique agency (alternative) | $14,000 | $22,000 | Higher confidence, higher cost |
| Claude Code + API (spec generation, QA assist) | $80 | $150 | Spec sprint + reviews |
| Apple Developer Program | $99 | $99 | Annual |
| Supabase Pro + Maps + EAS (3 months) | $400 | $600 | ~$150-200/mo |
| Beryl time — product direction + QA | 15 hrs | 25 hrs | Director role, not builder |
| TOTAL HARD CASH (LatAm team) | ~$6,600 | ~$13,000 | LatAm |
| TOTAL HARD CASH (US team) | ~$14,600 | ~$22,900 | US agency |

Margin on Package B Build We charge $30,000-39,000 over 3 months. With a LatAm team our hard cost is $6,600-$13,000 — leaving $17,000-$32,000 gross margin. With a US team: $14,600-$22,900 cost on $30,000-$39,000 billed = $7,000-$24,000 margin. The LatAm path is the high-margin play IF we can find a team that executes. This is where our AI-generated spec document is the difference-maker — a tight spec means less back-and-forth and less cost overrun on our side.

# Ongoing — What It Actually Costs vs. What We Charge

The retainer is where the real business is. Here is what $2,500/month actually costs to deliver, and what the margin looks like across both packages.

## Real Monthly Cost — $2,500/mo Retainer

| Cost Item | Low | High | Notes |
| --- | --- | --- | --- |
| Dev hours for bugs + light features | $600 | $1,200 | 6-10 hrs @ $80-120/hr |
| Supabase Pro | $25 | $25 | Monthly |
| Maps API (post-launch traffic) | $0 | $50 | Scales with usage |
| EAS Build credits | $0 | $29 | Per build cycle |
| Claude Code (QA assist, spec updates) | $10 | $30 | Ongoing usage |
| Beryl oversight time | 2 hrs | 4 hrs | Review + direction |
| TOTAL MONTHLY HARD COST | ~$635 | ~$1,334 |  |
| MARGIN on $2,500 retainer | $1,166 | $1,865 | 47-75% margin |

Key Insight on Retainer The retainer is the healthiest part of this engagement. $2,500/month with $600-$1,300 in real costs is a 47-75% margin business once the app is live. The goal is to get to launch and lock in a 3-month minimum. Every month after that is high-margin recurring revenue. This is why we don't discount the retainer — it's the asset.

## $5,000/mo Growth Retainer Margins

| Cost Item | Low | High | Notes |
| --- | --- | --- | --- |
| Dev hours (bugs + 1 feature sprint) | $1,600 | $3,000 | 20-30 hrs @ $80-100/hr |
| Infra (Supabase, Maps, EAS) | $75 | $150 | Scales with users |
| Claude Code + Beryl time | $50 | $100 | 4-6 hrs direction |
| TOTAL MONTHLY COST | ~$1,725 | ~$3,250 |  |
| MARGIN on $5,000 retainer | $1,750 | $3,275 | 35-65% margin |

# Beryl's Real Time Commitment

This is the honest accounting of what this engagement requires from Beryl personally — not what we tell the client, but what we need to plan around given Tu.Be, ZYVA, SGNL, Nordcom, MOZAIK, and the other active ventures.

## Package A — Owner Build Hours by Phase

| Phase | Weeks | Beryl Hours | What You're Actually Doing |
| --- | --- | --- | --- |
| Spec Sprint | 1-2 | 10-15 hrs | Feeding Cowork project, reviewing spec output, setting Supabase schema, writing acceptance criteria |
| Core Screen Build | 3-6 | 20-35 hrs | Active Claude Code sessions: 2-4 hrs/day during build weeks. This is the heavy phase. |
| Features + Polish | 7-9 | 10-15 hrs | Push notifications, edge cases, internal TestFlight testing on your own device |
| Contract Dev Handoff | 10-12 | 8-12 hrs | Onboarding contract dev, code review, App Store assets, metadata, screenshots |
| TOTAL BUILD HOURS | ~12 wks | 48-77 hrs | ~4-6 hrs/week average. Peak weeks (core build) will hit 10-15 hrs/week. |

Honest Assessment — Package A Time Risk 4-6 hrs/week is manageable IF the other ventures are in maintenance mode. If Tu.Be Studios is in active build phase, or SGNL is doing live trading reviews, or a ZYVA launch is happening simultaneously — Package A becomes a real squeeze. The decision gate at Week 7 (May 16) exists for this reason. If you're behind, flip to Package B immediately. Don't grind.

## Package B — Director Hours by Phase

| Phase | Weeks | Beryl Hours | What You're Actually Doing |
| --- | --- | --- | --- |
| Spec Sprint + Hiring | 1-2 | 12-18 hrs | Claude Code spec generation, interviewing devs, SOW negotiation, onboarding. Front-loaded. |
| Build Oversight | 3-10 | 1-2 hrs/wk | Weekly video review, async Slack/Telegram QA, approving merges. Very light once spec is tight. |
| App Store Prep | 10-11 | 3-5 hrs | Reviewing metadata, screenshots, App Store description. Claude Code assists. |
| Launch + Fanatics Fest | 12 | 3-5 hrs | Marketing collateral, QR codes, convention presence coordination |
| TOTAL BUILD HOURS | ~12 wks | 20-30 hrs | ~2 hrs/week average. Front-loaded in weeks 1-2. Very sustainable. |

## Ongoing Monthly Time (Both Packages)

| Activity | Hrs/Month | Notes |
| --- | --- | --- |
| Client check-in call (monthly) | 1 hr | Keep to 45-60 min. Async updates via Telegram between calls. |
| Review dev work + bug tickets | 1-2 hrs | Claude Code assists with QA — you approve, not debug. |
| Feature sprint direction (Growth tier) | 2-3 hrs | Only if client is on $5K/mo Growth retainer |
| TOTAL MONTHLY BERYL TIME | 2-6 hrs | Very lean once the system is running. Most retainer work is dev-led. |

# Pricing Logic & Margin Summary

Here is the full P&L view of both packages across 6 months, plus the reasoning behind why the prices are set where they are.

## Why $10,000 Build Is the Right Floor

- Below $10K signals we don't value the work — and clients who pay less tend to be more demanding

- The $10K number is psychologically a 'serious project' threshold for the collectibles market buyer

- Our hard cash cost on Package A is $2,730-$4,980 — the margin is real

- $10K also gives us runway to absorb a 2-week delay or one App Store rejection cycle without losing money

- Package B's $10-15K/month is justified because we're managing a team and delivering a fully-managed outcome — that's what agencies charge for this work

## Full 6-Month P&L — Both Packages

|  | Pkg A Revenue | Pkg A Cost | Pkg A Margin | Notes |
| --- | --- | --- | --- | --- |
| Build Phase (one-time) | $10,000 | $2,730-4,980 | $5,020-7,270 | Before owner time |
| Retainer × 3 months (min) | $7,500 | $1,905-4,002 | $3,498-5,595 | $635-1,334/mo cost |
| Infra pass-through (6mo) | Included | ~$800 | Absorbed | Built into pricing |
| 6-MONTH TOTAL — PACKAGE A | $17,500 | $5,435-9,782 | $7,718-12,065 | 44-69% margin |

|  | Pkg B Revenue | Pkg B Cost (LatAm) | Pkg B Margin | Notes |
| --- | --- | --- | --- | --- |
| Build Phase (3 months @ $10-13K/mo) | $30,000-39,000 | $6,600-13,000 | $17,000-32,000 | LatAm team |
| Retainer × 3 months ($2,500-5,000/mo) | $7,500-15,000 | $5,175-9,750 | $2,325-9,825 | Dev on retainer too |
| 6-MONTH TOTAL — PACKAGE B (LatAm) | $37,500-54,000 | $11,775-22,750 | $19,325-41,825 | 37-77% margin |

Margin Reality Check Package A is a good margin business IF we protect our time. The risk is scope creep on the retainer — a client who treats $2,500/month as unlimited access. The SOW must define what's in/out clearly, and we enforce it. Package B is the higher absolute dollar margin play, especially with a LatAm team. The spec document we generate with Claude Code is what makes Package B viable — without it, cost overruns on the dev team eat our margin.

# Risks We Own Internally

These are the real risk factors we need to account for — things we wouldn't say to a client but need to plan around.

## Technical Risks

- Claude Code output quality is not guaranteed — some screens may need significant rework before a real dev would be comfortable signing off on them

- Expo managed workflow works well for 80% of what TROV needs. The remaining 20% (custom push cert handling, deep link edge cases, background fetch) can hit unexpected walls

- App Store rejection cycles are unpredictable — Apple's review team is inconsistent. Budget time, not just money, for this.

- The Dream Experience feature and real-time alert system are the most complex parts of the v1 — these will take longer to rebuild natively than simpler screens

- Supabase real-time at scale can be tricky — if TROV gets meaningful traction at Fanatics Fest, we need to make sure the infra doesn't buckle

## Business Risks

- Scope creep on the retainer is the #1 margin killer — clients start treating monthly retainers as unlimited access once they're comfortable with us

- If Beryl's bandwidth drops mid-build on Package A, we may need to absorb the cost of converting to a dev team without repricing — plan for this

- The client (Brett/TROV) is also Beryl — this is a self-engagement, which means accountability structures need to be explicit to partners

- July 15 is hard. If the App Store rejects twice and we miss Fanatics Fest, there's reputational cost even if the contract is clean

- Finding a quality LatAm dev team fast (by Apr 10) requires starting NOW — the hiring process takes longer than people expect

## What We Do If Things Go Wrong

| Scenario | Our Response |
| --- | --- |
| Build is 3+ weeks behind by May 16 | Convert to Package B immediately. Use existing Claude Code output as spec + head start. No renegotiation needed if SOW has a conversion clause built in. |
| App Store rejects twice and we miss Jul 15 | Soft launch via TestFlight link at Fanatics Fest. QR code goes to TestFlight URL, not App Store. Continue App Store submission in parallel. Minimal reputational damage if we communicate proactively. |
| Dev team underperforms on Package B | Milestone-based SOW means we pay for deliverables, not time. If sprint 1 misses, we withhold month 2 payment and source backup. Budget a 2-week buffer in our project timeline for this. |
| Client wants features outside scope mid-retainer | Redirect to a separate sprint quote. Never absorb scope creep silently — it destroys the retainer margin and sets a bad precedent. |
| Supabase infra buckles at scale | Upgrade tier immediately. Cost is $200-400/month at scale — absorb in the first month, then pass to client as an infra fee or increase retainer by $200-300. |

# Partner Alignment — What We Need to Agree On

Before we present anything to the client side, these are the internal decisions that need to be locked.

## Decision 1: Which Package Do We Lead With?

- Package A is the honest recommendation IF Beryl has 4-6 hrs/week to commit during the build phase

- Package B is the right call given 7 active ventures — and it's the higher margin option with a LatAm team

- Recommendation: lead with Package B, offer Package A as the alternative for clients who push back on cost

- Never discount the build below $10K. That's the floor regardless of negotiation.

## Decision 2: Who Finds the Dev Team?

- This needs to be done this week regardless of which package we sell

- Start with Lemon.io and Expo Discord simultaneously — post the job today

- Interview 3-5 candidates, require: 2 App Store submissions to show, Expo+Supabase experience, fixed-scope only

- Budget: target $6,000-10,000 for the build on Package B with a LatAm team

## Decision 3: Retainer Scope Definition

Before we sign anything, we need a clear written scope for what $2,500/month includes. Suggested:

- Up to 8 hours of dev time per month (bug fixes, minor updates)

- Monthly check-in call (45 min)

- Push notification monitoring and uptime

- Response to App Store review requests or OS compatibility issues

- NOT included: new features, design changes, new screens, third-party integrations — these are quoted separately

## Decision 4: The TestFlight Fallback Plan

We need to decide now whether we'll offer a TestFlight soft launch at Fanatics Fest if App Store approval doesn't come through in time. Recommendation: yes, build this into the contract as a deliverable even if the App Store version isn't live yet. It protects us from the July 15 miss scenario and still delivers value at the convention.

⛔  CONFIDENTIAL — ANTIDOTE GROUP INTERNAL ONLY — NOT FOR CLIENT DISTRIBUTION  ⛔

TROV Internal Brief  |  March 2026